## Project Planner
Master thesis (156 days) Project Planner (168 days)
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Literature Research / Data collection | 1 | 21 | 1 | 20 | 20%
Data preprocessing | 1 | 32 | 1 | 31 | 45%
Start writing | 7 | 147 | 2 | 140 | 10%
Methodology design | 14 | 42 | 4 | 28 | 35%
Experiments | 31 | 122 | 4 | 91 | 60%
Finish first chapters of thesis | 50 | 110 | 4 | 60 | 54%
Refinement of methods and corrections | 1 | 121 | 5 | 120 | 63%
Finalise writing and presentation. | 120 | 125 | 5 | 5 | 100%
Milestone1: research proposal review | 1 | 2 | 5 | 1 | 0%
Milestone 2: Research plan review | 28 | 29 | 6 | 1 | 0%
Milestone 3: Research review. | 50 | 51 | 5 | 1 | 0%
Milestone: master thesis seminar (motivation, research goals, background) | 28 | 29 | 14 | 1 | 0%
Milestone: master thesis seminar | 90 | 91 | 14 | 1 | 0%
Milestone: approval version thesis | 135 | 136 | 14 | 1 | 95%
Milestone: permission for finalizing thesis | 142 | 143 | 15 | 1 | 100%
Milestone: Deadline final version thesis | 148 | 149 | 15 | 1 | 100%
Milestone: Deadline thesis presentation | 130 | 145 | 15 | 15 | 100%
Weekly meeting super visor | 1 | 168 | 1 | 168 | 100%
Milestone: graduation ceremony | 168 | 168 | 168 | 168 | 100%